## Arduino Project Timeline
No | Category | Resource Name | Description | Duration | Start | Finish | Precedence
1 | Arduino | Test Component Functionality | Ensuring all components can work properly. | 1 Day | 2021-01-16 | 2021-01-16 | 1
2 | Arduino | Assemble Robot Structure | Includes wiring kayout and strategic placement of sensors. | 1 Day | 2021-01-17 | 2021-01-17 | 2
3 | Arduino | Sensor Placement and Calibration | Able to detect the distances of objects. |  |  |  | 3
4 | Arduino | Motor Placement and Calibration | Able to travel in a straight line and steer 90 or 180 degrees. |  |  |  | 4
5 | Arduino | Link Arduino and Raspberry Pi communication | Able to send text based messages to each other. |  |  |  | 5
6 | Arduino | Create basic obstacle avoidance algorithm | To detect and successfully avoid obstacles when navigating.
7 | Arduino
8 | Arduino
9 | Arduino
10 | Arduino