## Arduino Project Timeline
No | Category | Resource Name | Description | Duration | Start | Finish | Precedence
1 | Arduino | Test Component Functionality | Ensuring all components can work properly. | 2 Days | 2021-01-16 | 2021-01-17 | 1
2 | Arduino | Assemble Robot Structure | Includes wiring kayout and strategic placement of sensors. | 2 Days | 2021-01-18 | 2021-01-19 | 2
3 | Arduino | Sensor Placement and Calibration | Able to detect the distances of objects. | 2 Days | 2021-01-20 | 2021-01-21 | 3
4 | Arduino | Motor Placement and Calibration | Able to travel in a straight line and steer 90 or 180 degrees. | 5 Days | 2021-01-22 | 2021-01-26 | 4
5 | Arduino | Link Arduino and Raspberry Pi communication | Able to send text based messages to each other over serial. | 3 Days | 2021-01-27 | 2021-01-29 | 5
6 | Arduino | Create basic obstacle avoidance algorithm | To detect and successfully avoid obstacles when navigating. | 2 Days | 2021-01-30 | 2021-01-31 | 6
7 | Arduino
8 | Arduino
9 | Arduino
10 | Arduino
11 | Arduino
12 | Arduino
13 | Arduino
14 | Arduino
15 | Arduino